## April 28
|  |  | Weekly Sprint Sheet |  | Team Members | Email
Project: Project 5 |  |  |  |  | Raja Patel | hpate85@uic.edu
Week Of: Week 17 |  |  | Team #10 |  | Tomas Kvapil | tkvapi2@uic.edu
[5 empty] | Damian Ortizflores | dortiz36@uic.edu
[5 empty] | Javier Rojas | jrojas39@uic.edu
Action Item | Item ID | Team Member | Last Week | This Week | Next Week | Issues
Update Server GUI | 10 | Damian | Set pictures on cards and store them into a data structure | Maybe think of something to do with this but not really a priority. | N/A
Update Client GUI | 10 | Damian | make sure we have multiple clients and we can match them uo randomally | Finishign touches on the GUI and having cards show up on all clients | N/A
Create New Deck | 10 | Raja | create a deck of all the cards so were not limited to just one deck and we can remove elements from the deck as we assign them to players | We need a way to create a new way of creating a new deck so that when client calls we can serve up a new deck with new cards | N/A
Game Logic | 10 | Tomas | Work with server to receive player choices and compare them and then assign pints base don the winner | Finish up making the game logic and how the game is technically played. Basically how the cards fight against each other | N/A
Reset the Game | 10 | Javier | figure out a way to pick 2 random players from the server and have them battle it out | After a client reaches 3 point, have the ability to start a fresh new game | N/A
Disable Card Order | 10 | Tomas | Work on GUI elements to figure out how they’ll work together and how well display information | Disable cards of players that are not in a battle as well as disable cards when a player has played their card | N/A
Setup point system | 10 | Raja | Work on GUI elements to figure out how they’ll work together and how well display information | Have all the players have points kept track and deciding on how we should have the points working | N/A
Update the winner | 10 | Damian | shoffle cards aso they are randomally assigned and then make sure when they are assigned they get removed from the deck | We need a winner for each battle and then finally a winner for the whole war. Think of a way to keep track display | N/A
Documentation | 10 | Raja/Javier | Get final description and sprint sheet together | Get the activity diagram and all the documentation together | N/A
Sever/Client Commucnication | 10 | Tomas | Getting basic foundations of back and forth communication | Sending all the server side information to the client and the having client sned their information to the server and updating the game. | N/A